## Sheet1
Sprint | Day | Impediments | Action Taken
Sprint 4 | Day 1 | Hugging Face translation API too slow | Switched to hybrid model with cached responses
Sprint 4 | Day 2 | Render deployment failed due to memory overload | Decided to offload heavy tasks to API endpoint
Sprint 4 | Day 3 | Audio output delay noticed | Implemented asynchronous streaming response
Sprint 4 | Day 4 | GPU access required for testing | Used Google Colab Pro instance temporarily