## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Team B | 2025-11-02 | Translation output missing final few seconds of audio | Sprint 4 | Arjun | Functional | Added audio padding to ensure full translation output | 2025-11-03 | Closed | Working fine after re-test
2 | Team B | 2025-11-03 | Render deployment fails due to high memory consumption | Sprint 4 | Arjun | Deployment | Switched to API-based processing instead of on-server translation | 2025-11-04 | Closed | Verified deployment success
3 | Team B | 2025-11-04 | Latency spikes after 3 minutes of streaming | Sprint 4 | Arjun | Performance | Added asynchronous buffering for smoother playback | 2025-11-05 | Closed | Latency improved by 40%
4 | Team B | 2025-11-06 | Audio-to-text model sometimes repeats words in translation | Sprint 4 | Arjun | AI Model | Adjusted Whisper parameters and normalized audio input | 2025-11-07 | Closed | Repetition issue resolved
5 | Team B | 2025-11-07 | Translated video output desynchronizes from audio | Sprint 4 | Arjun | Functional | Synced timestamps using MoviePy’s audio offset feature | 2025-11-08 | Closed | Output now properly synced
6 | Team B | 2025-11-09 | GPU dependency unavailable in Render environment | Sprint 4 | Arjun | Environment | Migrated heavy computation to Colab API | 2025-11-09 | Closed | Stable after environment switch
7 | Team B | 2025-11-10 | WebSocket breaks when input audio is longer than 8 minutes | Sprint 5 | Arjun | Performance | Implemented segmented streaming | 2025-11-11 | Open | Needs testing on 10+ min audio
8 | Team B | 2025-11-11 | Translation text shows wrong encoding for non-English languages | Sprint 5 | Arjun | Data Handling | Added UTF-8 normalization layer | 2025-11-12 | Closed | Encoding issue resolved successfully

## Sheet2
Logical
User Interface
Maintainability
Standards
Others